Minutes of meeting with LEI Thursday 25th of January, 2007 in Kaunas

Participants:

Jouzas Agustis, LEI

Vaclovas Miskinis , LEI (part of meeting)

One PhD-student from LEI

Hans Arvidsson, the Swedish Energy Agency/4C Strategies

Ragnar Smittberg, SecLink

1. General introduction of participants, purpose of meeting and agenda for day

2. Ragnar Smittberg(RS) gave overview information of the developments of the Understand project process from the meeting in Sundbyholm including the meeting in Stockholm on December 15 with NESA, Cranfield, the Swedish Energy Agency and SecLink.

3. Hans Arvidsson gave a presentation of the revised project scope, activities and end products. We also reviewed the “old” division of workdays according to work packages and participants. The following was agreed:

- Total number of workdays per participants has not been changed, however LEIs division of their 181 workdays will most likely be changed in the different work packages.

- LEI will develop suggestions on how best contribute to the revised project. Theses suggestions will be sent to project management(RS) as soon as possible. LEI will receive feedback on LEIs suggestions from project management and will then go on to develop a detailed work plan in - probably in collaboration with the different WP leaders (LEI does not have leadership in any specific WP). The detailed work plan will be presented at the meeting on May, 3-4, in Cranfield.

4. LEI received the project contract for reading. If approved, they will sign it and send it back to Ragnar. If they have questions, they will contact Ragnar.

5. LEI will receive a revised version of the project plan and minutes of this meeting.

6. Jouzas gave a general presentation of LEI and we made a short walk through the house and, after lunch, also through the beautiful city of Kaunas.

Minutes of,

Ragnar