Minutes of meeting with University of Zilina, Wednesday 28th of February 2007 in Zilina

Participants:

Jan Mikolaj, Zilina

Juraj Altus, Zilina

Michal Pokorny, Zilina

Hans Arvidsson, the Swedish Energy Agency/4C Strategies

Ragnar Smittberg, SecLink

1. General introduction of participants, purpose of meeting and agenda for day

2. Ragnar Smittberg (RS) gave overview information of the developments of the Understand project process from the meeting in Sundbyholm (November 2006) including the meeting in Stockholm on December 15, 2007 with NESA, University of Cranfield, the Swedish Energy Agency and SecLink.

3. Hans Arvidsson gave a presentation of the revised project scope, activities and expected end products. We also reviewed the “old” division of workdays according to work packages and participants. The following was agreed:

- Total number of workdays per participants has not been changed, however Zilinas division of their 95 workdays will most likely be changed in the different work packages.

- Zilina agreed to the new scope of the project. It was viewed as an improvement on the old scope.

- Hans stressed that there will be a first draft of the whitepaper by 16th of April and that it is now important that every partner will find how best provide its own resources to the overall Understand-project.

- Zilina will develop suggestions on how best contribute to the revised project. Theses suggestions will be sent to project management (RS) as soon as possible. Zilina will receive feedback on their suggestions from project management and will then go on to develop a detailed work plan - this in collaboration with the different WP leaders. The detailed work plan is th be presented at the meeting on May 3-4.

4. Zilina will receive these minutes of the meeting.

5. Jan delivered the Understand contract to Ragnar, but will send the bank sheet in special order as soon they have received it from Bratislava.

6. Slovensky elektroergeticky dispecing was visited and informed about the project – it met with acclaim from the management of the Slovak TSO.

Minutes of,

Ragnar